## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a project manager, I want to upload PDF, DOCX, CSV and TXT project documents so that the platform can read and extract text from all my project files. | MUST HAVE | none | Jeswitha | 3- Completed
Sprint 1 | Sprint 1 | US-02 | As a project manager, I want to select and upload several files at once and see which files were indexed and which failed, so that one bad file does not stop the others. | MUST HAVE | US-01 | Jeswitha | 3- Completed
Sprint 1 | Sprint 1 | US-03 | As a user, I want long documents split into overlapping chunks that keep sentences and CSV rows intact, so that search stays precise and no context is lost at chunk boundaries. | MUST HAVE | US-01 | Jeswitha | 3- Completed
Sprint 1 | Sprint 1 | US-04 | As a user, I want every chunk converted into an embedding and stored in a vector database separately for each project, so that documents can be searched by meaning. | MUST HAVE | US-03 | Jeswitha | 3- Completed
Sprint 1 | Sprint 1 | US-05 | As a user, I want to ask a question and get the most relevant chunks with their source file and similarity score, so that I can find project information quickly. | MUST HAVE | US-04 | Jeswitha | 3- Completed
Sprint 1 | Sprint 1 | US-06 | As a user, I want a simple web page where I can name my project, set chunk size, upload documents and ask questions, so that I can use the platform without writing code. | SHOULD HAVE | US-02, US-05 | Jeswitha | 3- Completed
Sprint 1 | Sprint 1 | US-07 | As a reviewer, I want to see a roadmap of all platform modules with their status, so that I can understand where Milestone 1 fits in the full platform. | COULD HAVE | US-06 | Jeswitha | 3- Completed
Sprint 1 | Sprint 1 | US-08 | As a team member, I want a design document with the system architecture, agent roles, RAG pipeline and data models, so that later milestones follow one clear plan. | MUST HAVE | none | Jeswitha | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US-08 | T-01 | Study RAG, multi-agent design patterns and project management basics. | 2026-10-05 | 2026-10-06 | Jeswitha | Others | 3- Completed | 1.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-02 | Design the system architecture, agent roles, RAG pipeline and data models; write the design document. | 2026-10-06 | 2026-10-07 | Jeswitha | Design | 3- Completed | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-03 | Create the project folder structure and the Document data model. | 2026-10-08 | 2026-10-08 | Jeswitha | Coding | 3- Completed | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-04 | Build the PDF parser and the DOCX parser (paragraphs and tables). | 2026-10-08 | 2026-10-09 | Jeswitha | Coding | 3- Completed | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
US-01 | T-05 | Build the CSV parser (rows as labelled sentences), the TXT parser and the single loader. | 2026-10-09 | 2026-10-09 | Jeswitha | Coding | 3- Completed | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
US-01 | T-06 | Unit test the parsers and loader with sample files, an empty file and an unsupported file type. | 2026-10-12 | 2026-10-12 | Jeswitha | Unit Test | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0
US-03 | T-07 | Build the chunker with overlap and test it on short and long documents. | 2026-10-12 | 2026-10-13 | Jeswitha | Coding | 3- Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0
US-04 | T-08 | Build the embedder (all-MiniLM-L6-v2) and the ChromaDB vector store with project filtering. | 2026-10-13 | 2026-10-14 | Jeswitha | Coding | 3- Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.5 | 0 | 0
US-05 | T-09 | Build the indexing script and the question search; test retrieval with sample questions. | 2026-10-14 | 2026-10-14 | Jeswitha | Unit Test | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
US-06 | T-10 | Build the Streamlit page with project name, chunk settings, upload tab and ask tab. | 2026-10-15 | 2026-10-15 | Jeswitha | Coding | 3- Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0
US-02 | T-11 | Add multi-file upload with a progress bar, per-file errors and a final summary. | 2026-10-15 | 2026-10-15 | Jeswitha | Coding | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
US-07 | T-12 | Add the platform roadmap tab showing the status of all modules. | 2026-10-16 | 2026-10-16 | Jeswitha | Coding | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
US-08 | T-13 | Fill the Agile, test plan and defect tracker templates; write the README and publish the code. | 2026-10-16 | 2026-10-16 | Jeswitha | Others | 3- Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 4 | While starting the ingestion code, commands such as pip install and python test files failed with 'No such file or directory', because the terminal was open in the outer project folder and not in the inner risk_advisor folder. | I moved into the inner risk_advisor folder with cd, confirmed the files with dir, and reopened VS Code on the inner folder so the terminal starts in the correct place.
Sprint 1 | Day 5 | test_loader.py was created in the wrong folder, so Python could not find it and the loader test did not run. | I moved the file into the risk_advisor folder and from then on created every new file inside that folder; the loader test then showed all four file types loading correctly.
Sprint 1 | Day 9 | Running streamlit run app.py failed with 'File does not exist: app.py' because the terminal was again in the outer folder. | I changed into the risk_advisor folder before running the command and the app started.
Sprint 1 | Day 9 | The Streamlit page stayed blank for a long time on start, because the heavy sentence-transformers library was loaded at start-up. | I moved the SentenceTransformer import inside the get_model() function, so the model loads only when the first document is indexed or the first question is asked.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-10-05 | 2026-10-16 | Jeswitha | Testing each module on its own sample file before starting the next one | Creating files and running commands from the wrong folder | Building one small module at a time and writing test cases as I go | Opened the inner risk_advisor folder in VS Code so the terminal starts in the right place; kept one sample file per file type for repeatable tests.
2
3
4
5
6
7