## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Kota Reddy Jeswitha | 2026-10-15 | The Streamlit page stayed blank for a long time after running the app, because the heavy sentence-transformers library was imported at start-up. | Sprint 1 | Jeswitha | User Interface | Moved the SentenceTransformer import inside get_model() in rag/embedder.py (lazy loading), so the page opens first and the model loads on the first index or question. | 2026-10-15 | Closed | Page now opens quickly; the one-time model load happens on the first Index or first question.
2 | Kota Reddy Jeswitha | 2026-10-16 | The Knowledge base section (document counters and indexed-documents table) was shown on the Upload tab, but the page should not display it. | Sprint 1 | Jeswitha | User Interface | Removed the Knowledge base block from the upload tab in app.py. The search and indexing code was not changed. | 2026-10-16 | Closed | Upload tab now shows only the uploader, the Index button and the per-file results.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others