# Weekly Team Meeting - Campus Event App

Date: 12 October 2026. Attendees: all four team members.

The backend developer reported that the login module is delayed because of exam preparation.

The team agreed that the payment gateway decision must be finalised before the next sprint.

Action items from this meeting are listed below.

| Action | Owner | Due |
| --- | --- | --- |
| Finalise payment gateway | Ravi | 20 Oct 2026 |
| Complete login module | Anita | 25 Oct 2026 |
| Clarify admin dashboard requirements | Team lead | 18 Oct 2026 |